## Project Plan
ID | Task Name | Start | Finish | Duration | Milestone | Predecessors
1 | 0. Pre-build & Authorisation |  |  | PT0H0M0S | Y
2 | Kickoff — project authorised |  |  | PT0H0M0S | Y
3 | Merge v3.7 spec amendment + correct typos |  |  | PT24H0M0S |  | 2
4 | Attorney review — disclaimer pack D-01 to D-12 |  |  | PT120H0M0S |  | 3
5 | Provision Keycloak, RabbitMQ, PostgreSQL, MinIO, K8s |  |  | PT80H0M0S |  | 3
6 | Select + integrate payment gateway sandbox |  |  | PT40H0M0S |  | 5
7 | Build readiness milestone |  |  | PT0H0M0S | Y | 4,5,6
8 | Phase 1 — Core Talent Pool + Auto-Application + Founder |  |  | PT0H0M0S | Y
9 | Apply DB migrations 001–015 + v3.7 additions |  |  | PT24H0M0S |  | 7
10 | Configure Keycloak realms (5 portals) |  |  | PT40H0M0S |  | 9
11 | Registration flows — Professional / Student / Business |  |  | PT56H0M0S |  | 10
12 | Founder Programme quota + race-condition serialisation |  |  | PT40H0M0S |  | 11
13 | Profile management — Professional + Student |  |  | PT64H0M0S |  | 11
14 | Business profile + recruitment request creation |  |  | PT48H0M0S |  | 13
15 | Compliance D-03 declaration + D-04 sensitive-filter flow |  |  | PT32H0M0S |  | 14
16 | Matching engine v1 — two-pass; standard weights |  |  | PT80H0M0S |  | 13
17 | Auto-Application audit ledger + opt-outs |  |  | PT40H0M0S |  | 16
18 | Anonymous shortlist preview UI |  |  | PT32H0M0S |  | 16
19 | Phase 1 test pack — quota race, perf, audit |  |  | PT56H0M0S |  | 12,17,18,15
20 | Phase 1 sign-off milestone |  |  | PT0H0M0S | Y | 19
21 | Phase 2 — Reporting, Payments, Notifications, Subscriptions |  |  | PT0H0M0S | Y
22 | Payment service — webhook + HMAC + PCI-DSS SAQ A |  |  | PT64H0M0S |  | 20
23 | Subscription tiers — Professional + Student + Business (4-tier) |  |  | PT56H0M0S |  | 22
24 | Report generation — PDF + Word + methodology disclosure |  |  | PT64H0M0S |  | 20
25 | D-02 v3.7 wording in report footer (post-attorney) |  |  | PT16H0M0S |  | 24,4
26 | Notification service — email + in-product (52+ triggers) |  |  | PT48H0M0S |  | 22
27 | Subscription reminder cron + deduplication |  |  | PT24H0M0S |  | 23
28 | Phase 2 test pack |  |  | PT40H0M0S |  | 25,26,27
29 | Phase 2 sign-off milestone |  |  | PT0H0M0S | Y | 28
30 | Phase 3 — Privacy, Compliance, Admin |  |  | PT0H0M0S | Y
31 | Candidate unlock flow + per-candidate billing |  |  | PT32H0M0S |  | 29
32 | Privacy controls — D-12 retention purge cron |  |  | PT32H0M0S |  | 29
33 | Admin Portal — analytics, refund processing |  |  | PT64H0M0S |  | 29
34 | Audit trail finalisation + immutability tests |  |  | PT32H0M0S |  | 33
35 | Phase 3 test pack |  |  | PT40H0M0S |  | 31,32,34
36 | Phase 3 sign-off milestone |  |  | PT0H0M0S | Y | 35
37 | Phase 4 — Internal Recruitment Link |  |  | PT0H0M0S | Y
38 | Internal portal — branded URL, token-secured |  |  | PT40H0M0S |  | 36
39 | Auto-close cron + matching pipeline trigger |  |  | PT32H0M0S |  | 38
40 | Consolidated invoice — portal + report (NAD 2,300) |  |  | PT24H0M0S |  | 39,22
41 | Phase 4 test pack |  |  | PT24H0M0S |  | 40
42 | Phase 4 sign-off milestone |  |  | PT0H0M0S | Y | 41
43 | Phase 5 — Student CSR + Social + Support Portal |  |  | PT0H0M0S | Y
44 | Student verification (3 methods) + grace + graduate upgrade |  |  | PT48H0M0S |  | 42
45 | F1 Public profile card + OG + PNG |  |  | PT40H0M0S |  | 44
46 | F2 Demand feed (anonymised) |  |  | PT24H0M0S |  | 44
47 | F3 Career Insights blog |  |  | PT32H0M0S |  | 44
48 | F4 + §26 Badge framework (Verified Student, Compliant Recruiter, Founder) |  |  | PT40H0M0S |  | 44
49 | F5 Graduate Spotlight (consent-gated) |  |  | PT24H0M0S |  | 45
50 | F7 Referral programme + reward application |  |  | PT32H0M0S |  | 44
51 | Support Portal — tickets, KB, identity verification |  |  | PT56H0M0S |  | 44
52 | Phase 5 test pack |  |  | PT40H0M0S |  | 45,46,47,48,49,50,51
53 | Phase 5 sign-off milestone |  |  | PT0H0M0S | Y | 52
54 | Phase 6 — AI Evolution + Assets + PWA + Assistant |  |  | PT0H0M0S | Y
55 | Adaptive weighting (custom_weights, sum-to-100, locked) |  |  | PT40H0M0S |  | 53
56 | Gap Analysis — 70–85% band sub-blocks (no AI in headings) |  |  | PT32H0M0S |  | 55
57 | RLHF data collection — match_feedback + day-14 prompt |  |  | PT40H0M0S |  | 55
58 | Asset management — logos + photo blind-screening |  |  | PT40H0M0S |  | 53
59 | PWA — manifest, service worker, offline, install |  |  | PT32H0M0S |  | 53
60 | AI Platform Assistant — 5 instances + post-gen filter |  |  | PT64H0M0S |  | 55
61 | Workforce Benchmarking Report (Business) |  |  | PT40H0M0S |  | 55
62 | F6 Employer reviews (moderated, ≥5 ratings) |  |  | PT32H0M0S |  | 53
63 | Phase 6 test pack — assistant identity, blind-screen, adaptive bounds |  |  | PT48H0M0S |  | 56,57,58,59,60,61,62
64 | Phase 6 sign-off milestone |  |  | PT0H0M0S | Y | 63
65 | Phase 7 — Video Integration (Premium) |  |  | PT0H0M0S | Y
66 | Video upload — 60s, 150 MB, virus scan |  |  | PT32H0M0S |  | 64
67 | Transcription provider integration |  |  | PT40H0M0S |  | 66
68 | Keyword extraction at 30% weight cap |  |  | PT24H0M0S |  | 67
69 | Content moderation queue |  |  | PT24H0M0S |  | 66
70 | Phase 7 test pack |  |  | PT24H0M0S |  | 68,69
71 | Phase 7 sign-off milestone |  |  | PT0H0M0S | Y | 70
72 | Phase 8 — RLHF Refinement + Marketplace (Future) |  |  | PT0H0M0S | Y
73 | Wait for 500 feedback records per scoring model |  |  | PT240H0M0S |  | 71
74 | Model weight refinement |  |  | PT120H0M0S |  | 73
75 | Marketplace expansion (scope TBD) |  |  | PT240H0M0S |  | 74
76 | Phase 8 sign-off milestone |  |  | PT0H0M0S | Y | 75
77 | SDLC Documentation (parallel, v2.0 population) |  |  | PT0H0M0S | Y
78 | Batches 1+2+3 populated — 53 docs |  |  | PT0H0M0S | Y | 2
79 | Batch 4 — folders 04, 05, 06, 10 |  |  | PT80H0M0S |  | 20
80 | Batch 5 — folders 07, 08 test plans |  |  | PT80H0M0S |  | 29
81 | Batch 6 — folders 11, 12 user manuals |  |  | PT64H0M0S |  | 36
82 | All 134 SDLC docs at v2.0 baseline |  |  | PT0H0M0S | Y | 79,80,81
83 | Pre-launch and Go-Live |  |  | PT0H0M0S | Y
84 | External penetration test |  |  | PT80H0M0S |  | 64
85 | UAT — Founder cohort |  |  | PT80H0M0S |  | 64
86 | Final attorney sign-off on disclaimer pack |  |  | PT40H0M0S |  | 4,82
87 | PRODUCTION GO-LIVE |  |  | PT0H0M0S | Y | 84,85,86

## Summary
Illumin360 Talent Match & Recruitment Platform — Project Plan v2.0
Author | Uriel Tapiwa Munjanga — Software Engineer & Architect
Company | Illumin Investments CC
Spec source | Illumin360 v3.7 Technical Specification
Source files | MSPDI XML opens directly in MS Project; File > Save As > .mpp
Phases | 8 plus pre-build and go-live streams
Tasks | 87
Resources | 8 — Architect, DevOps, DBA, QA, Legal, Marketing, Security, Sponsor
Start date | 19 May 2026
Open the 'Project Plan' sheet for the full WBS with dates.