ILLUMIN360

Talent Match & Recruitment Platform ¦ Namibia

PROJECT CHARTER

Document ID: ILLM-01-004 ¦ Version 1.0 ¦ April 2026 ¦ CONFIDENTIAL

| Project | Illumin360 — Talent Match & Recruitment Platform | Classification | CONFIDENTIAL |
| --- | --- | --- | --- |
| Organisation | Illumin Investments CC ¦ CC Reg: 2016/08234 ¦ VAT: 07851437-015 | Status | Draft for review — v2.0 |
| Author | Uriel Tapiwa Munjanga | Role / Title | Software Engineer & Architect |
| SDLC Phase | 01 — Project Initiation | Methodology | Waterfall |
| Predecessor Document | ILLM-01-003 — Stakeholder Register | Successor Document | ILLM-01-005 — Initial Risk Register |
| Review Required By | Project Manager ¦ Technical Lead ¦ Stakeholders | Sign-Off Authority | Project Sponsor ¦ CEO, Illumin Investments CC |

### Document Version History

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| 1.0 | April 2026 | Uriel Tapiwa Munjanga | Initial template created |
| 2.0 | 14 May 2026 | Uriel Tapiwa Munjanga | Populated from v3.7 spec. The charter formalises authority, scope, deliverables, timeline, budget, and governance. |

# 1. Document Introduction

📋 Guidance: This section introduces the document, its purpose, and its place in the Illumin360 SDLC. Complete all sub-sections before circulating for review.

| Document ID | ILLM-01-004 |
| --- | --- |
| Document Title | Project Charter |
| Project | Illumin360 — Talent Match & Recruitment Platform |
| SDLC Phase | 01 — Project Initiation |
| Methodology | Waterfall |
| Version | 1.0 |
| Date | April 2026 |
| Author | Uriel Tapiwa Munjanga ¦ Software Engineer & Architect |
| Predecessor | ILLM-01-003 — Stakeholder Register |
| Successor | ILLM-01-005 — Initial Risk Register |
| Review By | Project Manager ¦ Technical Lead ¦ Stakeholders |
| Sign-Off By | Project Sponsor ¦ CEO, Illumin Investments CC |
| Classification | CONFIDENTIAL |
| Status | TEMPLATE — Pending Completion |

## 2. Project Overview

Illumin360 is the Illumin Investments CC talent matching and recruitment platform for Namibia. It serves three customer segments (Professionals, Students, Businesses) through five portals (Professional, Student, Business, Administrator, Support) with the Auto-Application Engine as the defining feature.

| Item / Requirement | Detail / Description | Owner | Status |
| --- | --- | --- | --- |
| Project name | Illumin360 Talent Match & Recruitment Platform | — | Confirmed |
| Owner | Illumin Investments CC (CC 2016/08234, VAT 07851437-015) | — | Confirmed |
| Jurisdiction | Namibia | — | Confirmed |
| Sponsor | CEO, Illumin Investments CC | — | Confirmed |
| Architect | Uriel Tapiwa Munjanga | — | Confirmed |

## 3. Project Scope

Scope covers the build of all 5 portals, 13 microservices, and Phase 1 through Phase 7 of the 8-phase delivery plan. Phase 8 (RLHF model refinement + marketplace expansion) is out of scope for this charter and will be re-chartered when ready.

| Item / Requirement | Detail / Description | Owner | Status |
| --- | --- | --- | --- |
| In scope — portals | 5 portals: Professional, Student, Business, Administrator, Support | Architect | Confirmed |
| In scope — phases | Phase 1 through Phase 7 | PM | Confirmed |
| In scope — segments | 3 customer segments — Professionals, Students, Businesses | Marketing | Confirmed |
| Out of scope — Phase 8 | RLHF model refinement; marketplace expansion — separate charter | PM | Deferred |
| Out of scope — mobile native | PWA covers; native apps not in initial scope | PM | Deferred |
| Out of scope — ATS integration | Not in initial scope | PM | Deferred |

## 4. Project Deliverables

High-level deliverables. Detailed deliverables per phase in the Phase docs (folder 06).

| Item / Requirement | Detail / Description | Owner | Status |
| --- | --- | --- | --- |
| 134 SDLC documents populated to v2.0 | All folders 01–14 | Architect | In progress |
| Phase 1 build — Core Talent Pool + Auto-Application + Founder | Per ILLM-06-001 v2.0 | Architect | Pending |
| Phase 2 build — Reporting/Payments/Notifications/Subscriptions | Per ILLM-06-002 v2.0 | Architect | Pending |
| Phases 3–7 | Per ILLM-06-003 through ILLM-06-007 | Architect | Pending |
| Attorney-signed disclaimer pack | All 12 disclaimers reviewed before launch | Legal | Pending |
| Production deployment | Per ILLM-10-001 Deployment Plan v2.0 | DevOps | Pending |

## 5. Project Timeline

Eight-phase plan totalling 33–47 weeks per spec §27.

| Item / Requirement | Detail / Description | Owner | Status |
| --- | --- | --- | --- |
| Authorisation | On charter approval | Sponsor | Trigger |
| Phase 1 | Weeks 1–10 | Architect | Estimate |
| Phase 2 | Weeks 11–18 | Architect | Estimate |
| Phase 3 | Weeks 19–24 | Architect | Estimate |
| Phase 4 | Weeks 25–28 | Architect | Estimate |
| Phase 5 | Weeks 29–34 | Architect | Estimate |
| Phase 6 | Weeks 35–41 | Architect | Estimate |
| Phase 7 (premium) | Weeks 42–46 | Architect | Optional |

## 6. Project Budget

Detailed in ILLM-04-006 Budget Plan. Operating costs dominated by infrastructure and AI services. Build cost is sole-architect time plus required tooling.

| Item / Requirement | Detail / Description | Owner | Status |
| --- | --- | --- | --- |
| AI services Year 1 | ≈ NAD 77/month | Finance | Projected |
| Infrastructure | Hosting + Kubernetes capacity — TBC | DevOps | Estimate |
| Build cost | Architect time + tooling licences (mostly OSS — minimal) | Finance | Internal |
| External pentest pre-launch | Required — TBC vendor cost | Security | Required |
| Attorney review | Required — TBC fee | Legal | Required |

## 7. Project Team

Sole technical owner plus extended stakeholders.

| Item / Requirement | Detail / Description | Owner | Status |
| --- | --- | --- | --- |
| Architect (sole technical) | Uriel Tapiwa Munjanga | — | Active |
| Sponsor | CEO, Illumin Investments CC | — | Active |
| External attorney | TBD — Namibian | — | Engaged when ready |
| External security tester | TBD pre-launch | — | Engaged when ready |
| Operations (post-launch) | To recruit — Support staff for Phase 5 | — | Planned |

## 8. Governance Structure

Governance follows the Sponsor/Architect/Stakeholder model. Steering Committee, Project Team, and Client Reviews each have their own meeting minutes templates (ILLM-13-001 through ILLM-13-003).

| Item / Requirement | Detail / Description | Owner | Status |
| --- | --- | --- | --- |
| Sponsor | Decision authority, budget approval, strategic direction | — | Active |
| Architect | Technical authority, design, build, deployment | — | Active |
| Project Team meetings | Per ILLM-13-002 template | PM | Per-phase |
| Steering Committee | Per ILLM-13-001 template — quarterly | PM | Quarterly |
| Change Control | Per ILLM-11-005 and ILLM-13-005 | PM | Continuous |

## 9. Roles and Responsibilities

RACI for key activities.

| Item / Requirement | Detail / Description | Owner | Status |
| --- | --- | --- | --- |
| Authorise budget | Sponsor (A); Architect (R/C); — (I) | — | RACI |
| Approve architecture | Architect (R/A); Sponsor (C/I) | — | RACI |
| Approve disclaimer pack | Attorney (A); Architect (R); Sponsor (I) | — | RACI |
| Sign off Phase increments | Sponsor (A); Architect (R) | — | RACI |
| Operations post-launch | Operations (R); Sponsor (A); Architect (C) | — | RACI |

## 10. Approval

Charter signed by Sponsor authorises the build to commence.

| Item / Requirement | Detail / Description | Owner | Status |
| --- | --- | --- | --- |
| Sponsor | Authorise project | CEO Illumin Investments CC | Pending |
| Architect | Accept technical responsibility | Software Engineer & Architect | Drafted |

Document Sign-Off

| Prepared By | Uriel Tapiwa Munjanga ¦ Software Engineer & Architect |
| --- | --- |
| Reviewed By | [ Name, Title ] |
| Approved By | [ Name, Title ] |
| Review Date | [ DD Month YYYY ] |
| Approval Date | [ DD Month YYYY ] |
| Next Review | [ DD Month YYYY ] |
| Document Status | TEMPLATE — Pending Completion |

Illumin Investments CC  (CC Reg: 2016/08234  |  VAT: 07851437-015)  |  Trading as Illumin  |  Windhoek, Namibia  |  illumin360.com